## Retention ledger
Retention ledger
One row per contract. Retention held and Outstanding calculate themselves; fill in the rest. Delete the example row before you use it.
Project | Client | Contract sum | Retention percentage | Retention held | First moiety due | Second moiety due | Released | Outstanding | Notes
EXAMPLE ROW - delete this line | Example Client Ltd | 84000 | 5% |  | 2026-03-14 | 2027-03-14 | 2100 |  | First moiety paid on practical completion. Second moiety falls due twelve months later; chase it the week before. Illustrative figures.
Total | [8 empty] | The total includes the example row until you delete it.

## How to fill it in
How to fill it in
Every completed contract from the last few years, one to a row. Half an hour with your final accounts and your bank statements is usually enough to build the first version.
The columns
- | Project: what you call the job. Enough for you to find the file.
- | Client: who holds the money.
- | Contract sum: the final account figure where you have one, the order value where you do not.
- | Retention percentage: what the contract says, usually 3% or 5%. Type 5% or 0.05.
- | Retention held: calculated for you from the contract sum and the percentage.
- | First moiety due: usually half the retention, due at practical completion or the date your contract names.
- | Second moiety due: the balance, due at the end of the defects period. This is the one firms lose track of, because it falls a year or more after the job finished.
- | Released: what has actually reached your bank, not what was promised.
- | Outstanding: calculated for you. This column is the reason for the ledger.
- | Notes: the certificate number, the person who owes you the answer, the date you last chased. Write it here rather than remembering it.
What to do once it is filled in
- | Sort by Second moiety due. Anything with a date in the past is money you are owed now.
- | Put the future dates in your calendar with a reminder a fortnight before, so the request goes in before the date rather than months after it.
- | Where a release date has passed, ask in writing, quote the contract clause and the certificate, and keep the reply.
One caution
The Commercial Payments Bill would ban retention clauses in construction contracts after a transition period, with sums still held falling due by a fixed date. That makes this list more valuable, not less: money held under the old rules needs finding and documenting now.
The Commercial Desk - thecommercialdesk.co.uk